## Introduction
Contents | More resources
Key Roles | Microsoft Viva Adoption
Viva Connections | Microsoft Viva Learn documentation
Viva Engage | Microsoft Viva help and learning
Viva Goals
Viva Glint
Viva Insights
Viva Learning
Viva Pulse
Viva Topics
This workbook is an example project plan designed to help you begin your Microsoft Viva adoption journey. It includes example roles, project templates, and resources for the adoption of each Viva app. The Adoption Guides for each app provide a step-by-step walkthrough of the planning process and offer deeper insight into how to use the provided templates. You can find a link to each app’s Adoption Guide on its respective tab.

## Key Roles
Key Roles
Here are example key roles that are critical to a successful adoption effort. Identify contacts for each role and engage them early and often. Start by defining who will play which role in your organization, and then use the app specific tabs to assign tasks to the appropriate team member.
Role Definitions
Role | Viva Connections | Viva Engage | Viva Insights | Viva Glint | Viva Goals | Viva Learning | Viva Pulse | Viva Topics
Executive Sponsor | Communicate high-level vision and values of Viva Connections. Help identify and prioritize top HR needs. Connect regularly with HR and IT leaders across the organization. Actively participate in and use Viva Connections capabilities to help drive and reinforce adoption. | Communicate high-level vision and values of Viva Engage. Help identify and prioritize top HR needs. Connect regularly with HR and IT leaders across the organization. Actively participate in and use Viva Engage capabilities to help drive and reinforce adoption. | Communicate high-level vision and values of Viva Insights. Help identify and prioritize top HR needs. Connect regularly with HR and IT leaders across the organization. Actively participate in and use Viva Insights capabilities to help drive and reinforce adoption. | Communicate high-level vision and values of Viva Glint. Help identify and prioritize top HR needs. Connect regularly with HR and IT leaders across the organization. Actively participate in and use Viva Glint capabilities to help drive and reinforce adoption. | Communicates with leadership to embed OKRs into company culture. Drives company to center on OKRs, starting with modeling OKRs in key meetings and encouraging every member of the organization to be familiar with OKRs and be enrolled in the team effort to achieve them. | Communicate high-level vision and values of Viva Learning. Help identify and prioritize top HR needs. Connect regularly with HR and IT leaders across the organization. Actively participate in and use Viva Learning to help drive and reinforce adoption. | Communicate high-level vision and values of Viva Pulse. Help identify and prioritize top HR needs. Connect regularly with HR and IT leaders across the organization. Actively participate in and use Viva Pulse capabilities to help drive and reinforce adoption. | Communicate high-level vision and values of Viva Topics. Actively participate in and use Viva Topics to help drive and reinforce adoption.
Success Owner | Ensure the business goals are realized from adoption of Viva Connections. | Ensure the business goals are realized from adoption of Viva Engage. | Ensure the business goals are realized from adoption of Viva Insights. | Ensure the business goals are realized from adoption of Viva Glint | Ensure the business goals are realized from adoption of Viva Goals. | Ensure the business goals are realized from adoption of Viva Learning. | Ensure the business goals are realized from adoption of Viva Pulse. | Ensure the business goals are realized from adoption of Viva Topics.
Program Manager | Oversee Viva Connections deployment process and logistics. | Oversee Viva Engage deployment process and logistics. | Oversee Viva Insights deployment process and logistics. | Oversee Viva Glint deployment process and logistics | Oversee Viva Goals deployment process and logistics. | Oversee Viva Learning deployment process and logistics. | Oversee Viva Pulse deployment process and logistics. | Oversee Viva Topics deployment process and logistics.
Champions | Help evangelize Viva Connections and manage objection handling. | Help evangelize Viva Engage and manage objection handling. | Help evangelize Viva Insights and manage objection handling. | Help evangelize Viva Glint and manage objection handling. | See OKR Champion role | Help evangelize Viva Learning and manage objection handling. | Help evangelize Viva Pulse and manage objection handling. | Help evangelize Viva Topics and help their colleagues along the knowledge journey.
Training lead | Help train the early adopters and oversee training content. Could also be a Champion. | Help train the early adopters and oversee training content. Could also be a Champion. | Help train the early adopters and oversee training content. Could also be a Champion. | Help train the early adopters and oversee training content. Could also be a Champion. | Help train the early adopters and oversee training. Could also be OKR Champion. | Help train the early adopters and oversee training content. Could also be a Champion. | Help train the early adopters and oversee training content. Could also be a Champion. | Help train the early adopters and oversee training content. Could also be a Champion.
Department Leads (Stakeholders) | Identify how department will use Viva Connections and encourage engagement. | Identify how department will use Viva Engage and encourage engagement. | Identify how department will use Viva Insights and encourage engagement. | Identify how different departments/roles (People Analytics, Data Analytics, Employee experience, Talent and retention, DE&I) will use Viva Glint and encourage engagement | Drives progress against commits during planning process.. Maintains clarity against shared objectives/dependencies/priorities. Provides real-time adjustments on progress. | Identify how department will use Viva Learning and encourage engagement. | Identify how department will use Viva Pulse and encourage engagement. | Sponsor the rollout of Viva Topics and encourage engagement.
IT Specialists | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Connections into company technology stack. IT specialists must have necessary admin permissions to set up and configure the product. | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Engage into company technology stack. IT specialists must have necessary admin permissions to set up and configure the product. | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Insights into company technology stack. IT specialists must have necessary admin permissions to set up and configure the product. | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Glint into company technology stack. IT specialists/Viva Glint Admins must have necessary admin permissions to set up and configure the product. May include Viva Glint admins. | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Goals into company technology stack. IT specialists must have necessary admin permissions to set up and configure the product. | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Learning into company technology stack. IT specialists must have Microsoft Teams admin, Microsoft 365 global admin/SharePoint admin, and Knowledge admin permissions to set up and configure the product. | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Pulse into company technology stack. IT specialists must have necessary admin permissions to set up and configure the product. | Oversee all technical aspects of the setup, deployment, and rollout. Partner with HR to develop plan for fitting Viva Topics into company technology stack. IT specialists must have Microsoft Teams admin, Microsoft 365 global admin/SharePoint admin, and Knowledge admin permissions to set up and configure the product.
Communication Lead | Oversee company-wide communications about Viva Connections. | Oversee company-wide communications about Viva Engage. | Oversee company-wide communications about Viva Insights. | Oversee company-wide communications introducing Viva Glint | Oversee company-wide communications about Viva Goals. | Oversee company-wide communications about Viva Learning | Oversee company-wide communications about Viva Pulse | Oversee company-wide communications about Viva Topics
HR Manager | Help develop plan for how Viva Connections will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption. | Help develop plan for how Viva Engage will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption. | Help develop plan for how Viva Insights will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption. | Help develop plan for how Viva Glint will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption. | Help develop plan for how Viva Goals will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption. | Help develop plan for how Viva Learning will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption. | Help develop plan for how Viva Pulse will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption. | Help develop plan for how Viva Topics will fit into the rest of the employee ecosystem, inform company rollout, and drive adoption.
Community Managers | N/A | Manage day-to-day network activity; provide guidance and best practices | N/A | N/A | N/A | N/A | N/A | N/A
OKR Program Lead | N/A | N/A | N/A | N/A | Ensures that a clear plan and expections are in place, and that the business successfully realizes value from the launch. Facilities the OKR process, drives ownership and adoption across the organization. Has a hand in existing organizational planning and can dedicate ~50% of their time during launch period and 10-20% of time ongoing. | N/A | N/A | N/A
OKR Champions | N/A | N/A | N/A | N/A | Help with strategy execution and drive change across the organization. Spearhead their local programs and ensure checks and balances are in place for a successful rollout. Is involved in or leads planning processes for the teams they are partnering with and can dedicate 10-20% of their time ongoing. | N/A | N/A | N/A
Knowledge Administrator | N/A | N/A | N/A | N/A | N/A |  | N/A | Sets up Viva Topics experience
Knowledge Program Manager | N/A | N/A | N/A |  | N/A | N/A | N/A | Lead development of organization's knowledge strtegy, deliver on objectives, and chamption knowledge discovery across organization.
Contacts
Add the names of contacts for each role
Role | Viva Connections | Viva Engage | Viva Insights | Viva Glint | Viva Goals | Viva Learning | Viva Pulse | Viva Topics
Executive Sponsor | [Fill with contact names] | [Fill with contact names] | [Fill with contact names] | [Fill with contact names] | [Fill with contact names] | [Fill with contact names] | [Fill with contact names] | [Fill with contact names]
Success Owner
Program Manager
Champions
Training lead
Department Leads (Stakeholders)
IT Specialists
Communication Lead
HR Manager
Community Managers | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OKR Program Lead | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
OKR Champions | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
Knowledge Administrator | N/A | N/A | N/A | N/A | N/A |  | N/A
Knowledge Program Manager | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Viva Connections
Sample Plan for Viva Connections |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Identify core team and R&Rs | [Fill with role] | [Fill with date]
2 |  | Identify target scenarios
3 |  | Define success criteria and OKRs
4 | Assess | Assess organizational readiness
5 |  | Understand your environment and gaps
6 |  | Technical readiness checklist
6a |  | Complete legal & security review | [Fill with role]
6b |  | Review service capabilities with legal & security teams
6c |  | Decide guest access and provisioning policies
6d |  | Allow-list Microsoft 365 URL's & IP addresses
6e |  | Implement enterprise policies and Microsoft 365 group governance policies
6f |  | Assign report reader roles
6g |  | Complete network assessment (for Voice & Video services)
6h |  | Guest access Bandwidth planning
6i |  | Review minimum requirements spec and include mobile devices strategy
6j |  | Review Microsoft 365 Admin reporting tools
6k |  | Assign report reader role as needed
6l |  | Prepare help desk
7 | Deploy | Deployment resources
8 |  | Advanced Deployment Guides
9 | Train and adopt | Communication plan
10 |  | Training strategy
11 |  | Align training strategy to launch plan
12 | Drive value | Gather insights – monitor satisfaction and success metrics
13 |  | Reinforce adoption

## Viva Engage
Sample Plan for Viva Engage |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Identify core team and R&Rs | [Fill out with roles] | [Fill out with dates]
2 |  | Identify target scenarios
3 |  | Define success criteria and OKRs
4 | Assess | Assess organizational readiness
5 |  | Understand your environment and gaps
6 |  | Technical readiness checklist
6a |  | Complete legal & security review
6b |  | Review service capabilities with legal & security teams
6c |  | Decide guest access and provisioning policies
6d |  | All-list Microsoft 365 URL's & IP addresses
6e |  | Implement enterprise policies and Microsoft 365 group governance policies
6f |  | Develop usage policy and guidance that aligns with company policy, code of conduct, and culture
6g |  | Set up keyword monitoring, report conversation, and other governance processes
6h |  | Identify mobile device and remote connectivity strategy
6i |  | Determine IT standards around email archives, file retention, and external sharing policies.
6j |  | Review Microsoft 365 Admin reporting
6k |  | Review Microsoft 365 Admin reporting tools. Assign report reader role as needed
6l |  | Prepare help desk
7 | Deploy | Deployment resources
8 |  | Advanced Deployment Guides
9 | Train and adopt | Communication plan
10 |  | Training strategy
11 |  | Align training strategy to launch plan
12 | Drive value | Gather insights – monitor satisfaction and success metrics
13 |  | Reinforce adoption

## Viva Glint
Sample Plan for Viva Glint |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Identify core team and roles and responsibilities | [Fill out with roles] | [Fill out with dates]
2 |  | Define success criteria program goals, and OKRs
3 |  | Align communication plan
4 | Assess | Take inventory of current investments & determine gaps
5 |  | How feedback is currently solicited
5a |  | Current channels for feedback
5b |  | Manager access to survey results
5c |  | Barriers to employee feedback
5d |  | Employee concerns with anonymity
5e |  | Available survey languages
5f |  | Technical readiness checklist
6 |  | Complete training for project role
6a |  | Configure company structure and setup
6b |  | Confirm and configure survey access methods
6c |  | Determine survey and dashboard languages
6d |  | Configure and send user data (attributes and hierarchy configurations
6e |  | Identify survey cadence
6f |  | Configure approved sender list and test users
6g |  | Assign roles and permissions
6h |  | Review test dashboard for attribute preview
6i |  | Review action plan content
6j |  | Complete legal & security review
6k |  | Implement enterprise policies and Microsoft 365 group governance policies
6l |  | Prepare help desk
7 | Deploy | Organizational communications
8 |  | Teaser campaign
9 |  | Launch campaign
10 |  | Survey launch
11 | Train and adopt | Communication plan
12 |  | Training strategy
13 |  | Gather insights
14 |  | Execute action plans
15 | Drive value | Reinforce adoption
16 |  | Update examples and training often
17 |  | Highlight positive results from Viva Glint feedback
18 |  | Teach managers how to leverage Viva Glint to take actions with their teams
19 |  | Continue to find your Champions - advocates for change - including executives, managers, and admins
20 |  | Report on action plans, success criteria, OKRs, and business success

## Viva Goals
Sample Plan for Viva Goals |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Identify and engage key stakeholders | [Fill out with roles] | [Fill out with dates]
2 |  | Get executive sponsorship
3 |  | Surface early constraints (budget, bandwidth, priorities)
4 |  | Establish goal-setting cadences and rhythm of business (ROB)
5 |  | Establish community
6 | Assess | Assess organizational readiness
7 |  | Understand your environment and gaps
8 |  | Technical readiness checklist
8a |  | Complete legal & security review
8b |  | Review service capabilities with legal & security teams
8c |  | Decide guest access and provisioning policies
8d |  | Allow-list Microsoft 365 URL's & IP addresses
8e |  | Implement enterprise policies and Microsoft 365 group governance policies
8f |  | Review minimum requirements spec and include mobile devices strategy
8g |  | Review Microsoft 365 Admin reporting tools
8h |  | Prepare help desk
9 | Deploy | Draft and enter org-level goals
10 |  | Draft and enter team goals
11 | Train and adopt | Communication plan
12 |  | Training strategy
13 |  | Align training strategy to launch plan
14 | Drive value | Gather insights – monitor satisfaction and success metrics
15 |  | Reinforce adoption

## Viva Insights
Sample Plan for Viva Insights |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Identify core team and R&Rs | [Fill out with roles] | [Fill out with dates]
2 |  | Identify target scenarios
3 |  | Define success criteria and OKRs
4 | Assess | Assess organizational readiness
5 |  | Understand your environment and gaps
6 |  | Technical readiness checklist
6a |  | Complete legal & security review
6b |  | Review service capabilities with legal & security teams
6c |  | Understand the different Viva Insights roles and access levels
6d |  | Identify the appropriate rollout scenario
6e |  | Set the Viva Insights configuration to identify which elements users have access to
6f |  | Run a pilot rollout
6g |  | Assess the pilot lessons to inform larger organizational rollout
6h |  | Assign licenses to users in Microsoft 365
6i |  | Configure the access at the tenant level
6j |  | Prepare help desk
7 | Deploy | Deployment resources
8 |  | Advanced Deployment Guides
9 | Train and adopt | Communication plan
10 |  | Training strategy
11 |  | Align training strategy to launch plan
12 | Drive value | Gather insights – monitor satisfaction and success metrics
13 |  | Reinforce adoption

## Viva Learning
Sample Plan for Viva Learning |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Align stakeholders and assign core team and R&Rs | [Fill out with roles] | [Fill out with dates]
2 |  | Understand learning source connections
3 |  | Develop learning ecosystem strategy
4 | Assess | Understand your current learning ecosystem and gaps
5 |  | Define success criteria and OKRs
6 |  | Technical readiness checklist
6a |  | Complete legal & security review
6b |  | Review service capabilities with legal & security teams
6c |  | Decide guest access and provisioning policies
6d |  | Allow-list Microsoft 365 URL's & IP addresses
6e |  | Implement enterprise policies and Microsoft 365 group governance policies
6f |  | Assign report reader roles
6g |  | Complete network assessment (for Voice & Video services)
6h |  | Guest access Bandwidth planning
6i |  | Review minimum requirements spec and include mobile devices strategy
6j |  | Review Microsoft 365 Admin reporting tools
6k |  | Assign report reader role as needed
6l |  | Prepare help desk
7 | Deploy | Understand access requirements
8 |  | Set up and configure Viva Learning
9 | Train and adopt | Communication plan
10 |  | Training strategy
11 |  | Drive a learning culture
12 | Drive value | Gather insights – monitor satisfaction and success metrics
13 |  | Reinforce adoption

## Viva Pulse
Sample Plan for Viva Pulse |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Identify core team and R&Rs | [Fill out with roles] | [Fill out with dates]
2 |  | Identify target scenarios
3 |  | Define success criteria and OKRs
4 | Assess | Assess organizational readiness
5 |  | Understand your environment and gaps
6 |  | Technical readiness checklist
6a |  | Complete legal & security review
6b |  | Assign Viva Pulse admin roles
6c |  | Pin Viva Pulse in Microsoft Teams
6d |  | Enable Teams Activity feed notifications
6e |  | Customize privacy policy link
6f |  | Check diagnostic data settings
6g |  | Modify customization and notification options
7 | Deploy | Deployment resources
8 |  | Advanced Deployment Guides
9 | Train and adopt | Communication plan
10 |  | Training strategy
11 |  | Align training strategy to launch plan
12 | Drive value | Gather insights – monitor satisfaction and success metrics
13 |  | Reinforce adoption

## Viva Topics
Sample Plan for Viva Topics |  |  |  | Resources
Adoption Guide
Admin/Operator documentation
|  |  | Key Roles | End User documentation
Order | Step | Task | Role Assign tasks to roles defined on the Key Roles tab | Target Completion
1 | Plan | Identify core team and R&Rs | [Fill out with roles] | [Fill out with dates]
2 |  | Identify and define scenarios
3 |  | Define knowledge team roles
4 |  | Select rollout approach
5 |  | Conduct feature discovery
6 |  | Identify topic source sites and flag sensitive content
7 |  | Define knowledge metrics
8 | Assess | Assess organizational readiness
9 |  | Conduct culture assessment to select curation method
10 |  | Understand your environment and gaps
11 |  | Technical readiness checklist
11a |  | Complete legal & security review
11b |  | Review service capabilities with legal & security teams
11c |  | Review Microsoft Viva Topics security and privacy
11d |  | Review and understand Search security and configuration
11e |  | Consider Microsoft 365 Groups and Teams to make sure they are set as public or private groups or teams
11f |  | Review use of "everyone," "everyone except external users," and broad security groups. Work with site owners to correct permission configuration if inappropriate content is visible.
11g |  | Exclude sensitive SharePoint sites from topics discovery so that content in these sites will appear in topic experiences
11h |  | Exclude topics by name so they do not appear in topic experiences.
11i |  | Consider using sensitivity labels or data loss prevention to restrict access to content and access reviews to periodically review user access to sensitive information.Microsoft 365 Groups and Teams to make sure they are set as public or private groups or teams
11j |  | Consider using SharePoint taxonomy terms to create topics.
11k |  | Prepare help desk
12 | Deploy | Assign Viva Topics licenses, configure Viva Topics
13 |  | Advanced Deployment Guides
14 | Train and adopt | Create communication plan
15 |  | Create and implement training strategy
16 |  | Create knowledge community of practice in Viva Engage to enable Knowledge Managers and Champs to share best practices
17 |  | Align training strategy to launch plan
18 | Drive value | Gather insights – monitor satisfaction and success metrics
19 |  | Reinforce adoption